## Invoice
[Your Business Name] |  |  | INVOICE
[Street address, City, State ZIP] |  | Invoice no. |  |  | INV-0001
[email@yourbusiness.com] |  | Invoice date |  |  | 2026-10-14 12:00
[Phone] |  | Due date |  |  | 2026-10-29 12:00
BILL TO |  |  | PROJECT
[Customer Name] |  |  | Kitchen remodel
[Billing address] |  |  | PROJECT ADDRESS
[customer@email.com] |  |  | 64 Summit Avenue, Denver, CO
CONTRACT / PO NO.
C-2026-041
BILLING PERIOD
Phase 2 of 4
DESCRIPTION | QTY | RATE | TAX % | AMOUNT | TAX
Phase 2 - rough framing and blocking (milestone) | 1 | 6800 |  | 6800 | 0
Rough electrical and plumbing (subcontracted) | 1 | 4200 |  | 4200 | 0
Lumber and framing materials | 1 | 2350 | 8% | 2350 | 188
Change order #2 - add pantry wall | 1 | 1150 |  | 1150 | 0
|  | Subtotal |  | 14500
|  | Discount |  | 0
|  | Tax |  | 188
|  | Total |  | 14688
|  | Amount paid |  | 0
|  | Balance due |  | 14688
NOTES |  | TERMS & CONDITIONS
Phase 2 complete and passed rough inspection on Oct 9. Phase 3 (drywall and cabinets) starts Oct 20. |  | Payment due within 15 days. Contract value $48,000; billed to date including this invoice: $26,500.
Replace the bracketed text and the sample lines with your own. Prices are fictional. Sample tax applies to parts and materials only; check what is taxable in your state. Edit the tinted cells; Amount, Tax and the totals calculate. Enter tax as a percentage (8%).